## Task Tracker
AI Job Agent — Project Task Tracker ¦ 2-Week Sprint
Status Legend: |  | To Do |  | In Progress |  | Done ✓ |  | Blocked
# | Phase | Task | Description | Assigned To | Week | Day Start | Day End | Priority | Status | Notes | GitHub Issue
1 | 🔧 Setup | Project setup & repo structure | Init GitHub repo, folder structure, virtual env, requirements.txt, README | Member 1 | W1 | Day 1 | Day 1 | High | To Do |  | #issue-1
2 | 🔧 Setup | Define data models & schemas | Design Resume, Job, User, SkillGap Pydantic models used across the project | Member 2 | W1 | Day 1 | Day 2 | High | To Do |  | #issue-2
3 | 📄 Resume | Resume upload endpoint (FastAPI) | POST /resume/upload — accept PDF/DOCX, save to disk, return file ID | Member 1 | W1 | Day 2 | Day 3 | High | To Do |  | #issue-3
4 | 📄 Resume | parse_resume() tool | Extract name, skills, experience, education from uploaded file using LLM | Member 1 | W1 | Day 3 | Day 4 | High | To Do |  | #issue-4
5 | 💼 Job | Job description input endpoint | POST /job/analyze — accept raw JD text, store, return job ID | Member 2 | W1 | Day 2 | Day 3 | High | To Do |  | #issue-5
6 | 💼 Job | analyze_job_posting() tool | Extract required skills, experience level, responsibilities from JD using LLM | Member 2 | W1 | Day 3 | Day 4 | High | To Do |  | #issue-6
7 | 🤖 Agent | Single agent scaffold (LangGraph) | Build base agent graph with state, entry point, tool-calling loop | Member 3 | W1 | Day 2 | Day 4 | High | To Do |  | #issue-7
8 | 🤖 Agent | match_resume_to_job() tool | Compare parsed resume vs job requirements, return match score + gaps list | Member 3 | W1 | Day 4 | Day 5 | High | To Do |  | #issue-8
9 | 🗄️ Backend | FastAPI app skeleton | Create main.py, routers, CORS, health check endpoint, env config | Member 4 | W1 | Day 1 | Day 2 | High | To Do |  | #issue-9
10 | 🗄️ Backend | PostgreSQL schema & connection | Create tables: users, resumes, jobs, sessions. Set up SQLAlchemy or psycopg2 | Member 4 | W1 | Day 2 | Day 4 | High | To Do |  | #issue-10
11 | 🧠 RAG | Vector DB setup (Chroma/FAISS) | Initialize vector store, embed resume best-practices & sample JDs | Member 3 | W1 | Day 4 | Day 5 | Medium | To Do |  | #issue-11
12 | 💡 Feedback | generate_resume_feedback() tool | Use LLM + RAG to produce structured feedback: structure, content, alignment | Member 1 | W1 | Day 5 | Day 7 | High | To Do |  | #issue-12
13 | 💡 Feedback | rewrite_resume_bullets() tool | Generate 3-5 improved bullet points per job section tailored to target JD | Member 1 | W2 | Day 8 | Day 9 | High | To Do |  | #issue-13
14 | 📚 Learning | recommend_learning_path() tool | Map skill gaps → recommended courses/resources from bootcamp catalog | Member 2 | W2 | Day 8 | Day 9 | High | To Do |  | #issue-14
15 | 🎤 Interview | generate_interview_questions() tool | Generate role-specific behavioral + technical questions based on JD | Member 2 | W2 | Day 9 | Day 10 | High | To Do |  | #issue-15
16 | 🤖 Agent | Agent routing & decision logic | Agent decides which tool to call based on user intent (clarify, review, prep) | Member 3 | W2 | Day 8 | Day 9 | High | To Do |  | #issue-16
17 | 🧠 RAG | RAG integration across tools | Wire vector store retrieval into feedback, learning, interview tools | Member 3 | W2 | Day 9 | Day 10 | Medium | To Do |  | #issue-17
18 | 🧠 Memory | Short-term session memory | Store current resume, job, feedback in agent state between turns | Member 4 | W2 | Day 8 | Day 9 | High | To Do |  | #issue-18
19 | 🧠 Memory | Long-term user profile (DB) | Persist goals, skill gaps, recommendations to PostgreSQL across sessions | Member 4 | W2 | Day 9 | Day 10 | Medium | To Do |  | #issue-19
20 | 🖥️ UI | Chat interface (Streamlit/Gradio) | Build chat UI: file upload, text input, display agent responses, history | Member 1 | W2 | Day 10 | Day 11 | High | To Do |  | #issue-20
21 | 🖥️ UI | API integration & end-to-end flow | Connect UI → FastAPI → Agent → Tools, test full user journey | Member 2 | W2 | Day 10 | Day 11 | High | To Do |  | #issue-21
22 | 🧪 Testing | Unit tests for tools | Write pytest tests for parse_resume, match_resume_to_job, feedback tools | Member 3 | W2 | Day 10 | Day 11 | Medium | To Do |  | #issue-22
23 | 🧪 Testing | End-to-end integration test | Run full flow: upload CV → match JD → feedback → interview Qs → verify output | Member 4 | W2 | Day 11 | Day 12 | High | To Do |  | #issue-23
24 | 🚀 Delivery | README & documentation | Write setup instructions, architecture diagram, usage examples, demo steps | Member 1 | W2 | Day 12 | Day 13 | High | To Do |  | #issue-24
25 | 🚀 Delivery | Demo preparation & final review | Prepare demo script, fix last bugs, clean repo, tag release v1.0 | All | W2 | Day 13 | Day 14 | High | To Do |  | #issue-25

## Team Overview
Team Overview — Who Owns What
Member | Focus Area | Key Tasks | Week | Status
Member 1 | Resume & UI | parse_resume, generate_resume_feedback, rewrite_resume_bullets, Chat UI, README | W1+W2 | To Do
Member 2 | Job & Learning | analyze_job_posting, Job endpoint, recommend_learning_path, generate_interview_questions, API integration | W1+W2 | To Do
Member 3 | Agent & RAG | Agent scaffold, match_resume_to_job, RAG setup, routing logic, unit tests | W1+W2 | To Do
Member 4 | Backend & Memory | FastAPI skeleton, PostgreSQL schema, session memory, long-term user profile, integration test | W1+W2 | To Do

## Timeline
2-Week Timeline (Days 1–14)
Task | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
Project setup & repo structure | █
Define data models & schemas | █ | █
Resume upload endpoint (FastAPI) |  | █ | █
parse_resume() tool |  |  | █ | █
Job description input endpoint |  | █ | █
analyze_job_posting() tool |  |  | █ | █
Single agent scaffold (LangGraph |  | █ | █ | █
match_resume_to_job() tool |  |  |  | █ | █
FastAPI app skeleton | █ | █
PostgreSQL schema & connection |  | █ | █ | █
Vector DB setup (Chroma/FAISS) |  |  |  | █ | █
generate_resume_feedback() tool |  |  |  |  | █ | █ | █
rewrite_resume_bullets() tool | [7 empty] | █ | █
recommend_learning_path() tool | [7 empty] | █ | █
generate_interview_questions() t | [8 empty] | █ | █
Agent routing & decision logic | [7 empty] | █ | █
RAG integration across tools | [8 empty] | █ | █
Short-term session memory | [7 empty] | █ | █
Long-term user profile (DB) | [8 empty] | █ | █
Chat interface (Streamlit/Gradio | [9 empty] | █ | █
API integration & end-to-end flo | [9 empty] | █ | █
Unit tests for tools | [9 empty] | █ | █
End-to-end integration test | [10 empty] | █ | █
README & documentation | [11 empty] | █ | █
Demo preparation & final review | [12 empty] | █ | █